Project Number: RAS5056

Title: Supporting Mutation Breeding Approaches to Develop New Crop Varieties Adaptable to Climate Change

Classification: New

FOA: 20 - Crop production

Justification:

Beneficiaries: Not only the farming community but also consumers will benefit from the introduction and dissemination of the fertigation technology, which will enhance ecosystem service efficiency, reduce environmental pollution and reduce costs through improved efficiency. The private sector, who is involved in drip irrigation and fertilizer distribution, will be also engaged.

Strategy: The project will provide technical support to enhance national and regional capacities, through regional training courses, expert missions and technical meetings. Regional training and information will be provided on the use of fertigation technologies. This will be distributed at the national level by the National Team, who will devise their own national strategies with regard to the institutes, policy makers, extension agencies, and farmers.

Sustainability:

Objective: To enhance people's livelihood through the improvement of crop productivity and food security through the application mutation technique and other nuclear and isotopic techniques under the driver of climate change and variability

Logical Framework Matrix (LFM)

|  | Design Element | Indicator | Means of Verification | Assumptions |
| --- | --- | --- | --- | --- |
| Outcome | Enhancement of national and regional capacities of RCA member states for application of mutation and other nuclear and isotopic techniques to develop and pilot test of new crop varieties adaptable to climate change | Nuclear related technology is recognized and incorporated in national plans for identification and selection of suitable plant varieties | national reports | Technology packages widely distributed to farmers and acceptance by farmers. |
| Output | 1 Effective project implementation and coordination | Planned activities are effectively implemented as scheduled and within available budget | project achievement report | There is no significant policy changes that could effect project implementation |
|  | 2 Training materials on the use of mutation techniques and biotechnology for routine application in identifying desirable crop characteristics and breeding new mutant varieties | Training materials for regional use available in 2015 | training materials | MS are willing to adopt the materials for subsequent use in their national programmes |
|  | 3 Trained personnel in the areas of mutagenesis approaches and nuclear and isotopic techniques for evaluating soil and water use efficiencies to improve crop plant tolerant to main biotic and abiotic stresses. | At least 4 personnel from each participating country benefit from the RTCs | Project achievement report | Trained personnel continue their responsibilities and able to apply the knowledge gained |
|  | 4 Strengthened cooperation among the RCA member states and potential partners, including a functional Oceania Association of Plant Mutagenesis (AOAPM) | Project activities and results are recognized and known by potential partners | project progress reports | Suitable mechanisms initiated to sustain the cooperation |
|  | 5 New mutant crop varieties identified and tested for productivity, resource use efficiencies and tolerence to abiotic stress under large field demonstration and/or commercialization across the region | At least 3 mutant varieties identified by end of the project | Achievement report | national efforts continue to extend the use of mutant varieties with interest of end users |
| Activity | 1.1 Plan and implement project project activities | Regional and national work plan presented and agreed at the Coordination meeting | adopted work plans | participating countries keep their strong commitment and interest for effective project implementation |
|  | 2.1 Review and develop training materials related to mutation techniques | Existing materials timely collected and compiled by NPCs | progress reports | The materials will be distributed and used by concerned authorities at the national and regional level |
|  | 2.2 Review, update and adopt training materials for use in the RTCs | Revised draft training materials available end 2012 | Draft training materials | The materials will be distributed and used by concerned authorities at the national and regional level |
|  | 3.1 Enhance technical capacities through regional training courses and technical meetings related to mutation breeding and efficiency use of soil and water resources | Regional training courses conducted as scheduled | agreed training plan | Trained personnel are given authorities to utilize the knowledge gained for effective implementation of project activities |
|  | 4.1 Provide technical support for launching and function of AOAPM upon decision of the RCA member states | Operation plan developed and discussed at the Coordination meeting | Meeting report | MS continue to support successful launching and operation of the Association |
|  | 4.2 Implement activities to support cooperation with potential partners, including FNCA | Collaborative activities identified at the Coordination meeting and incorporated in the project work plan | Progress report | other potential partners are willing to share expertise and knowledge with RCA members |
|  | 5.1 Conduct national surveys for the identification and selection of existing advanced mutated lines and/or mutant varieties better suited to to be used in the project based on their agronomic traits and/or adaptability to harsh environments | NPCs National surveys conducted before the Coordination meeting | Meeting report | Existing data and information available and accessible |
|  | 5.2 Conduct national demonstrations of technology packages developed for end users | Details of national demonstration plans presented and discussed at the Coordination meeting | Meeting report | Sufficient resources are provided by the government |
| Input | 1.1.1 Project Planning and Coordination Meeting | Meeting information sheet prepared and circulated at least 3 months in advance | Meeting report | All NPCs are able to attend |
|  | 1.1.2 Mid-Term Project Assessment meeting | Meeting information sheet prepared and circulated at least 3 months in advance | Meeting report | All NPCs are able to attend |
|  | 1.1.3 Final Project Assessment Meeting | Meeting information sheet prepared and circulated at least 3 months in advance | Meeting report | All NPCs are able to attend |
|  | 1.1.4 EM: expert mission to support national activities | Suitable expert timely identified and recruited | EM report | Expert available as and when required and NPCs prepare plans to receive the expert. |
|  | 2.1.1 Review and revise training materials for adoption and used by all participating countries as regional materials | Suitable experts identified, and Terms of Reference timely formulated | progress report | MS are willing to use the materials for national training |
|  | 2.2.1 Technical meeting to assess existing training materials on suitable approaches to improve the selected crops for adaptation to main effects of climate change; prepare an outline specific contents and structure for improvement | Meeting information sheet prepared and circulated at least 3 months in advance | Meeting report | existing materials are available for use |
|  | 2.2.2 Prepared updated training materials for review and adoption by RCA member states | list of existing materials compiled by Q3 of 2012 | Compiled information |  |
|  | 3.1.1 RTC: Regional training courses on train-trainers on the application of molecular markers to mutation breeding and the use of nuclear and isotopic techniques in assessment of soil and water efficiency use | Training prospectus prepared and circulated at least 3 months in advance | Training report | trained personnel remain on duties and utilize and share the knowledge gained from the RTC with others |
|  | 3.1.2 Technical meeting on mutation breeding, in combination with participation in the international Symposium on induced mutations on plants | Meeting information sheet prepared and circulated at least 3 months in advance | Meeting report | Identified experts are able to participate and contribute for successful meeting |
|  | 3.1.3 RTC: Regional training course on the application of molecular markers to mutation breeding programme with focus on traits contributing to better adaptation (disease and/or abiotic stress resistance) | Training prospectus prepared and circulated at least 3 months in advance | Training report | trained personnel remain on duties and utilize and share the knowledge gained from the RTC with others |
|  | 3.1.4 RTC: Regional training course on the use of nuclear and isotopic techniques in assessment of fertilizer and water use efficiency | Training prospectus prepared and circulated at least 3 months in advance | training report | trained personnel remain on duties and utilize and share the knowledge gained from the RTC with others |
|  | 3.1.5 RTC: Regional training course in the use of C-13 in soil organic matter studies and in assessment of plant tolerance to abiotic stress (drought and salinity0 | Training prospectus prepared and circulated at least 3 months in advance | Training report | trained personnel remain on duties and utilize and share the knowledge gained from the RTC with others |
|  | 4.1.1 EM: expert mission to support AOAPM | Suitable expert timely identified and recruited | EM report | Expert available as and when required and NPCs prepare plans to receive the expert. |
|  | 4.1.2 Launching of the Association, in connection with project meeting | MS' agreement discussed at the Project Coordination meeting | Meeting report | MS keep commitment to operate the Association and enable to mobilize funding by themselves for implementing the planned activities |
|  | 4.2.1 Implement collaborative activities for exchange of expertise as well as present and disseminate project implementation with potential partners | Plan of activities discussed and agreed at the Coordination Meeting | progress report | Initial cooperation maintained and sustained by concerned stakeholders |
|  | 4.2.2 Disseminate project activities and exchange of expertise with potential partner organizations, including FNCA | Plan of activities discussed and agreed at the Coordination Meeting | project progress report | Initial cooperation maintained and sustained by concerned stakeholders |
|  | 4.2.3 Implement collaborative activities to extend and dissemination project results and establish collaboration with other partner agencies | activities implemented as planned | progress report | Initial cooperation maintained and sustained by concerned stakeholders |
|  | 5.1.1 Conduct national surveys of existing advanced mutated lines and/or mutant varieties for identification and selection for use in the project. Compiled data/information is to be discussed at the Project Planning and Coordination meeting | Survey outline developed, NPCs timely initiate and conduct the surveys | NPCs' report and presentation | NPCs have sufficient capacities and required resources to conduct the survey |
|  | 5.2.1 National field trial demonstration integrating soil and water management practices of mutant varieties developed for end users | Tentative plan for national trial demonstration presented by NPC at the Coordination meeting | Meeting report | NPCs have sufficient capacities and required resources to conduct national trial demonstrations |
|  | 5.2.2 National activities to promote the transfer of developed mutant varieties and soil & water management to end users including extension services | Tentative plan for national trial demonstration presented by NPC at the Coordination meeting | progress report | NPCs have sufficient capacities and required resources to conduct national trial demonstrations |
|  | 5.2.3 EM: expert mission to support national activities | Suitable expert timely identified and recruited | EM report | Expert available as and when required and NPCs prepare plans to receive the expert. |
|  | 5.2.4 EM: expert mission to support national activities | Suitable expert timely identified and recruited | EM report | Expert available as and when required and NPCs prepare plans to receive the expert. |